## Stakeholder Register Solution
Stakeholder Register Format: Annual New Investor Dinner Event
Name/Position | Organization | Role | R | A | C | I | Comments
Martha Wilson / COO | Operations | Sponsor |  | X | X | X | Approves budget and agenda
Sidney Morris / Project Manager | Operations | Lead Project Manager | X | X |  |  | Leads and coordinates event
Evan Anthony / Finance Manager | Finance | Financial Management & Compliance | X |  | X | X | Ensures budget compliance
Sunny James / HR Training Manager | HR | Training Management | X |  | X | X | Supports employee prep
Ram Evans / HR Customer Liaison | HR | Primary Customer Liaison |  |  | X | X | Handles RSVPs and investor relations
Noriko Tanaka / Marketing & IT Manager | Marketing/IT | Marketing Manager/IT Liaison |  |  | X | X | Manages promotion, IT/AV
Raj Adams / Operations Team | Operations | Logistics Planning and Execution | X |  |  |  | Logistics tasks
Mary Kim / Operations Team | Operations | Operations Planning | X |  |  |  | Operational support tasks
John Kowalski / Operations Team | Operations | Logistics Planning and Execution | X |  |  |  | Setup and logistics
Priya Madison/CEO | ABC Investment LLC | Keynote Speaker |  |  | X | X | Keynote, reputation at stake
External Speakers | Partner Vendor | Subject Matter Experts (SME) |  |  | X | X | Share various investment topics
Restaurant Manager | Partner Vendor | Restaurant Manager | X |  | X | X | Provides restaurant, catering, parking
RACI Terms Defined | ROLE | DEFINED |  |  |  | Version: 1 Mar 20xx
| R | Responsible for performing work or tasks
| A | Accountable for outcomes
| C | Consult as a Subject Matter Expert (SME)
| I | Inform as project progresses