This lab demonstrates how to leverage Generative AI to transition into a new project role quickly. By analyzing the Fleet Ease Logistics transcript, we can convert unstructured dialogue into the three formal deliverables required by your Sponsor.

As a professional already working with agentic workflows and data integration, you can think of the AI here as a "Requirements Parser" that structures human intent into actionable project metadata.

### Part III: Step 1 – Identified and Classified Requirements

| Requirement | Category | Description / Metric |
| --- | --- | --- |
| Late Delivery Reduction | Business | Reduce late deliveries by 20%. |
| Customer Satisfaction | Business | Improve customer satisfaction scores by 15%. |
| Dispatcher Productivity | Business | Increase dispatcher productivity by 25%. |
| Real-time Optimization | Functional | System must provide real-time route optimization for dispatchers. |
| Push Notifications | Functional | Drivers must receive push notifications for route changes. |
| Offline Functionality | Functional | App must maintain core functionality in areas with poor connectivity. |
| Performance Dashboard | Functional | Provide a real-time dashboard for monitoring delivery efficiency. |
| Simple UI | Functional | Driver interface must allow "one-tap" acknowledgement of updates. |
| System Integration | Non-Functional | Seamless connection with existing ERP and dispatch platforms. |
| Availability | Non-Functional | Maintain 99.9% system uptime. |
| Data Security | Non-Functional | All data must be encrypted at all times. |
| Data Migration | Transition | Migrate all necessary records from the legacy system. |
| Pilot Program | Transition | Conduct a 30-day pilot before the full rollout. |
| Training & Support | Transition | Provide training for drivers/dispatchers and helpdesk support during rollout. |

### Part IV: Step 2 – Project Activity Timeline

| Phase | Activity | Duration | Dependencies |
| --- | --- | --- | --- |
| Planning | Stakeholder Alignment & Final Scope | 2 Weeks | None |
| Design | UI/UX Design (One-tap interface) & Architecture | 4 Weeks | Planning |
| Development | API Integration (ERP) & Core Optimization Engine | 8 Weeks | Design |
| Testing | Security Audit (Encryption) & UAT | 3 Weeks | Development |
| Pilot | 30-Day Guided Field Pilot | 4 Weeks | Testing, Data Migration |
| Launch | Full Rollout & Helpdesk Support Setup | 2 Weeks | Pilot Success |

### Part V: Step 3 – Risk Analysis List

| Risk Description | Probability | Impact | Recommended Response |
| --- | --- | --- | --- |
| Data Migration Errors | Medium | High | Perform multiple test migrations and data validation audits before the pilot. |
| Integration Failure (ERP) | Medium | High | Establish early "sandbox" testing with IT Lead Priya to verify API stability. |
| Driver Resistance to UI | High | Medium | Involve Cal (Driver Rep) in weekly UI reviews to ensure "one-tap" simplicity. |
| Connectivity Dead Zones | High | Medium | Rigorous testing of "Offline Mode" to ensure data syncs once signal returns. |
| Security Breach/Data Leak | Low | High | Implement end-to-end encryption and conduct third-party penetration testing. |
| Late Delivery Metrics Not Met | Medium | High | Iteratively tune the optimization algorithm based on real-time pilot data. |
| System Downtime during Rollout | Low | High | Establish a 24/7 helpdesk and a predefined rollback plan for the first 48 hours. |
| Inadequate Staff Training | Medium | Medium | Develop "quick-start" guides and mandatory hands-on sessions for dispatchers. |

### Reflective Insight for Your Portfolio:

Using AI for this task allowed you to move from a raw transcript to a structured project charter in minutes. However, as noted in your User Summary, your expertise in Cybersecurity and Zero Trust Architecture should be used to "double-check" the AI's Non-Functional requirements—specifically ensuring the "encryption at all times" requirement meets modern industry standards.

Venkatesh, you have officially completed the lab! Would you like to see how these requirements would look if we converted them into "User Stories" for an Agile Sprint?