# Retrospectives and Post-Mortem Templates

Estimated duration: 4 minutes

### Learning objectives:

By the end of this reading, you will be able to:

- Explain the purpose of retrospectives and post-mortems in post-deployment workflows

- Describe the roles of architects in facilitating cross-functional feedback sessions

- Document technical issues, impacts, and lessons learned using structured templates

- Create actionable follow-up plans with assigned owners and measurable outcomes

## Introduction

Once a software system goes live, the work doesn't end; it evolves continuously. Architects play a critical role in post-deployment learning, helping teams reflect on what went well, what went wrong, and what needs improvement.

This reading includes two sample templates: one for a retrospective and one for a post-mortem review. These are real-world documents that solutions architects might lead or contribute to following a major release or incident.

Each includes sample fields and example entries from a fictional logistics company, SkyFleet Logistics, based on their launch of a new vehicle tracking system.

The final column in each table provides architect comments, offering guidance on how these templates support cross-functional improvement.

## Template 1: Retrospective summary

Event: Launch of SkyFleet's Real-Time Vehicle Tracking Dashboard

Facilitated by: Solutions Architect

Date: 03 August 2025

Attendees: Product Owner, QA Lead, DevOps Manager, Customer Support Rep

| Section | Entry | Architect comments |
| --- | --- | --- |
| What went well? | - Real-time data updates performed accurately - Training material was well received | Good to highlight successes from both technical and user-facing perspectives. |
| What didn't go well? | - Notification delays due to backend latency - Inconsistent tracking in 2 regions | Suggest creating action items linked to these problems for better traceability. |
| What can we improve? | - Coordinate earlier with the infrastructure team - Include regional QA in UAT | Recommend assigning owners to each improvement point. |
| Action items | - Re-test tracking module with new data set (Owner: QA) - Add regional logs to alert system (Owner: DevOps) | Ensure that owners and deadlines are captured clearly. |
| Next retrospective date | 31 August 2025 | Helps create a culture of continuous feedback, not one-off sessions. |

## Template 2: Post-mortem review

Event: Tracking System Outage (3-Hour Downtime in Eastern Region)

Facilitated by: Solutions Architect

Date: 11 August 2025

Attendees: QA, DevOps, Product, Support

| Section | Entry | Architect comments |
| --- | --- | --- |
| Incident summary | Vehicle tracking data was unavailable from 11:00 to 14:00 in the Eastern Region. | Keep this brief and factual. |
| Root cause | Missing index on location table caused high query latency during peak load. | Clear technical cause-great start. Also note detection time if available. |
| Impact | Dispatch delays reported by 4 clients; 12 support tickets filed. | Quantifying impact helps business teams understand the incident's reach. |
| Detection & response time | Detected at 11:20 AM; partial recovery by 1:30 PM; full recovery by 2:00 PM. | Timeline is critical - helps evaluate monitoring effectiveness. |
| Lessons learned | - Indexing strategy needs review - Alert thresholds missed early warning signs | Architect can help turn these into checklist items for future deployments. |
| Follow-up actions | - Add monitoring for slow queries (Owner: DevOps) - Revisit indexing best practices (Owner: DBA) | Make sure every action has an owner and due date. |

## How to use these templates

Use the retrospective summary:

- After a successful release

- As part of sprint closing sessions

- To identify positive patterns and collaboration gaps

Use the post-mortem review:

- After any outage, delay, or critical issue

- To surface root causes and prevent recurrence

- To promote a transparent, blame-free review culture

## Summary

In this reading, you learned that:

- Retrospectives help teams celebrate wins and identify opportunities for smoother collaboration

- Post-mortems focus on root cause analysis and action planning after technical failures

- Architect-led templates bring structure and accountability to improvement processes

- Clear action items with owners and dates are essential for closing the feedback loop

Whether you're facilitating or contributing, your job as an architect is to turn insights into progress, making every deployment better than the last.